## Sheet1
STATE ACTION ON BUSINESS ENABLING REFORMS (SABER) PROGRESS REPORT SOKOTO STATE 2024
Original action plan as published | [9 empty] | Progress Update
S/N | Business Enabling Reform Areas | Reform Objectives | Action Steps | Description and Key Targets | Responsible MDA | Contributing MDAs | Budget | Planned Start Date | Planned End Date | Status | Description of Status | Next Steps
| The focus area for the reforms eg transparency of official fees and procedures | What the State intends to achieve by implementing the Business Enabling Reform | Very detailed, step by step process on how the objective will be achieved | User, beneficiaries, recipient of the reform Explain actions and/or sub-actions and include targets | One MDA responsible for the action/activity | Supporting MDAs | Estimated budget for the action/activity | When you commit to start the implementation of the actions | When you commit to complete the actions and achieve your targets | Indicate whether the action/activity is completed, ongoing - on time, ongoing - delayed or dropped | Describe the status of each action, explaining reasons for any delays or actions being dropped. Explain any changes that occurred during implementation affecting start and end dates | Describe next steps for the outstanding actions. For example, is the action getting carried over to the following year's action plan?
1 | Improved Land Administration and Land Investment Process | 1. Enhance the transparency and efficiency of registering and administering land titles. 2. Improve land administration and increase land investments in agriculture. | Equipped Sokoto Geographic Information System with required infrastructures to enable the digital process of land Administration to deliver effective Service | 1. Streamline the processes for obtaining CofOs and Building Permits and publish processes, timelines and fees on the Ministry of Lands and Surveys & URPB websites 2. Drive online payment of fees and submission of forms. 3. Creation of a data-centric digital archive of CofOs and building permits with a searchable index | Ministry of Lands and Housing, Urban and Regional Planning Board (URPB) | SOIRS | Yet to Get Actual | 01/01/2024 | 31/12/2024 | Completed Impact:The reform has improved transparency and efficiency in the registration and administration of land titles, leading to better land governance and increased investment in land within the state. | i. Sokoto State Geographical Information System (SOGIS) has been fully equipped with the necessary infrastructure to support the digital transformation of land administration processes. ii. Fee payments and form submissions can now be completed online in real time, improving accessibility and efficiency. iii. A data-centric digital archive with a searchable index has been created for Certificates of Occupancy (CofOs) and building permits, enhancing record management and transparency. | i. Reduce the processing time for obtaining Certificates of Occupancy (CofOs) to 60 days (2 months). ii. Ensure that Building Permits are processed within 24 hours. iii. Improve the accuracy of the CofO issuance process to at least 90%. iv. Enhance and fully digitize the CofO archive system to achieve 100% data-centric record management.
2 | Increased fiber optic network deployment and access to broadband | Improve the chances of receiving investments by making the process of obtaining Right of Way (ROW) transparent, affordable and accountable. | 1. Compile and publish on the state official website: the process for obtaining ROW including all relevant MDAs, timeframes, and costs. | Transparency and accountability in the process of ROW with official information online on process for obtaining ROW to guide potential investors | SSURPB | MCIT, Ministry of Works, Ministry of Science, Technology & Innovations, IRS | 1. Forms For Application N50,000. 2. Approval Forms N250,0003. Computer Accessories N100,000. 4. Plane Sheets A4 N20,000. 5. File Jackets N50,000. 6. Hp Laptop 4 Pieces. 7. Other Office ;Accessories N500,000 8, Color Printer N 200,000 = N3,120,000 | 01/01/2024 | 31 28/12/2024 | Completed. Impact:The reform has enhanced the state's ability to attract investment by making the process of obtaining Right of Way (RoW) more transparent, affordable, and accountable. | The compilation and publishing of the State Official website for obtaining RoW including all relevant MDAs time freme and cost has been sins concluded. | i. Ensure that all relevant revenue payments are completed within 7 days. Ii. Process and issue the required permits within 21 days of application.
3 | Increased Sustainable Large-Scale Investments | Stimulate sustainable large-scale investments through public-private partnerships and robust investment promotion framework. . | 1. Strengthen technical Public-Private Partnership Policy (PPP) coordination to facilitate investments, particularly with the green economic zone. 2. Strengthen and expand investment promotion services. 3. Amend the IPA law to further strengthen investment promotion coordination. | A published pipeline of large-scale public-private collaborations in Sokoto State. Issue an executive order to mandate the investment co. to coordinate investment promotion. | Sokoto Investment Co, SBPP | State House of Assembly, Ministry of Justice, Chamber of Commerce | N1,870,000.00 | 30/1/2024 | 31/12/2024 | Ongoing. The reform has begun to stimulate large scale investment through Public Private Partnership (PPP) and robust investment promotion framework through an executive order mandating Sokoto investment company to perform the role of IPA pending the conclusion of the IPA law currently in progress. | i. The State Government has strengthened technical coordination of its Public-Private Partnership (PPP) Policy, particularly to support investment opportunities in the Green Economic Zone. ii. Investment Promotion Services have been expanded and reinforced, enhancing the state's capacity to attract and support investors. iii. The Investment Promotion Agency (IPA) Law is currently in progress. The process has experienced some delays due to staff and management changes at the Sokoto Investment Company, which plays a key role in driving the IPA initiative. | i. Identify potential Public-Private Partnership (PPP) projects across relevant Ministries, Departments, and Agencies (MDAs). ii. Initiate the funding application process for the selected PPP projects. iii. Obtain formal approval from the Governor to proceed with implementation.
4 | Enabling Firm Operations and Regulatory Reforms | Increase transparency, accountability, and efficiency in service delivery of five BEE state MDAs while promoting openness. | 1. State Government to mandate Five BEEs: BPP, SOWB, URPB, IRS & MCIT to publish their processes, fees, and service level agreements (SLAs). 2. The Five BEEs to institute and adopt Grievance Redress Mechanism that will ensure fulfilment of obligations. | The government will issue an executive order to mandate the five BEEs to ensure they fulfil their obligations to the private sector in line with established service level agreements and continually communicate to ease the experience of businesses and investors. | Ministry of Justice | SBPP, SOWB, URPB, IRS & MCIT, Ministry of Agriculture | (1) Gazetting of five (5) Executive Orders 300 copies of each Executive Orders at the rate of #1,000 per copy. Each Executive Order is = #1,000 x 300 copies = #300,000. Five (5) Executive orders = #300,000 x 5 = #1,500,000 (2)2HP Laptops = #1,000,000 (3) Stationeries = #100,000 (4) Miscellaneous = #100,000 TOTAL #2,700,000 | 02/06/2024 | 31/12/2024 | Completed. Impact: The reform has improved transparency, accountability, and efficiency in the delivery of the Five BEEs, while fostering greater openness in government processes across the state. | i. The State Government has issued a directive to the Five BEEs — BPP, SOWB, URPB, IRS, and MCIT — to publish their procedures, applicable fees, and Service Level Agreements (SLAs) to enhance transparency. ii. The Five BEEs are required to establish and adopt a functional Grievance Redress Mechanism to ensure accountability and timely resolution of service-related complaints. | i. Ensure that Business Premises Registration is processed and issued within 24 hours. ii. Facilitate the issuance of BPP (Bureau of Public Procurement) clearance and certificates within 48 hours (2 days). iii. Ensure Water Board permits are obtainable within 48 hours. iv. Enable real-time issuance of Revenue Clearance Certificates. v. Ensure that Urban and Regional Planning Board certifications are processed and issued within 48 hours. vi. Strengthen the responsiveness of the Business Enabling Environment (BEE) MDAs to promptly address and resolve grievances raised by business owners.
|  | Developing guidelines to enhance trade and promote exports from the state | 1. Develop the state export strategy and guidelines | A purposeful, clear and focused path towards boosting trade activities and proceeds for the state. | Ministry of Commerce, Trade and Industry, Sokoto | Ministry of Agriculture, Internal Revenue Sevice, SCEP | 100000000 | 04/02/2024 | 31/7/2024 | Completed. Impact: The reform has led to the development of clear guidelines that support trade activities and encourage export growth within the state. | The State Export Strategy and Guidelines have been successfully developed, providing a clear framework to promote and support export activities within the state. | i. Identify and register approximately 170 exporters across the state. Ii. Ensure that the exporter registration process is completed within 24 hours. Iii. Enable exporters to generate and access their certificates online for ease and efficiency.
5 | Quick determination of commercial disputes | Establish and operationalize small claims commercial courts to improve access to commercial courts and offer alternative, prompt dispute resolution. | 1.To set up the judicial committee and establish small claims courts. | The establishment and operationalisation of a minimum of two small claims courts. | State High Court | Ministry of Justice. IRS. | Yet to Get actual | 01/01/2024 | 31/12/2024 | Completed. Impact: The establishment and operationalization of Small Claims Commercial Courts has significantly improved access to justice for resolving commercial disputes, especially for small businesses and individuals. Implication: This means that parties now have a faster, more affordable, and simplified legal avenue to settle business-related disagreements. It also reduces the burden on regular courts and encourages the use of alternative dispute resolution mechanisms, promoting a more business-friendly environment. | i. Approximately 40 cases have been successfully dispensed through the Small Claims Court, with the resolution time, including appeals- reduced to 60 days. This has boosted the confidence of business owners by ensuring quicker and more efficient access to justice. | i. Target the resolution of at least 100 cases through the Small Claims Courts within the year. ii. Reduce the trial and appeal resolution timeline to 60 days to ensure faster access to justice. iii. Strengthen public confidence in the justice system by ensuring timely and fair handling of commercial disputes.