## Progress Report
STATE ACTION ON BUSINESS ENABLING REFORMS (SABER) PROGRESS REPORT 2025
Original action plan as published | [9 empty] | Progress Update
S/N | Business Enabling Reform Areas | Reform Objectives | Action Steps | Description and Key Targets | Responsible MDA | Contributing MDAs | Budget | Planned Start Date | Planned End Date | Status | Description of Status | Next Steps
1 | Improved Land Administratio n and Land Investment Process | 1).Enhance the transparency and efficiency of registering and administering Certfiicate of Occupancy CofOs with the use of advanced technology. 2). Improve land Investment in Agriculture, Industry and Housing in the State. | i. Maitain the use of Ministry of Land and Sokoto Geographical Information System (SOGIS) websites for regsitration and other land administration in obtaining CofOs. ii. Create a user frindly application system data base for Digital land Tittles. ii. Training Relevant personel (10 Personel). iv. Monitored and evaluate the system operations | i. Reduced processing time for obtaining CofOs from 120 Days to to 60 Days ie 2 Months. ii. Improved accuracy of CofOs processing atleast 90% accurecy. iii. Improved data-centric digital archive of CofOs and building permit by 100%. iv. 100% new CofOs registred during 2025 (1st Jnanuary, 2025 to 31st December, 2025) Digitalized and Indexed on ongoing basis. | Ministry of Land Housing and Survey, Sokoto Geograpgical Information Systeme (SOGIS) | Sokoto Urban and Regional Planning Baord (SURPB), Sokoto Board of Internal Revenue. | 150000000 | 1st January 2025 | 31 Decemeber 2025 | Completed | i. CofOs processing reduce to 30 Days. Ii. We have achieved 90% of accurecy in processing CofOs iii. Our data-centric digital archieve and building permit are now 100%. Iv. All CofOs registered from 1st January to 31st December are successfully digitalized and indexed. | The processing of obtaining CofOs is projected to be reduce from 30 Days to 2 weeks.
2 | Increase Fibre Optic Network Deployment and Access to | Increase the chances of receiving investment by making the | To compile and publish on the state official website the processes of obtaining ROW including all relevant MDAs time | Transparency and accountability in the processes of ROW with official information online on processes for | Sokoto Urban and regional Planning Board (SUPB) | 1. Ministry of Commers, Trade and Industry. 2. Ministry of Works, | 10000000 | 1st January 2025 | 31 Decemeber 2025 | Completed | All processess of obtaining ROW are accessible and process online with utmost transperency and accountability, as well as all revenue payments are now processed online. | Our plan is to generate ROW Certificate online at your comport zone
| Broadband | process of obtaining Rigth of Way (ROW) transparent affordable and | frames and cost. | obtaining ROW to continue to guide potential investors. 1)All relevant payments of revenue should |  | 3.Ministry of Science and Technology 4. Ministry of Innovation and
3 | Increase substainable large scale Investrment | Stimulate sustaininable large scale investment through Public Private Partnership (PPP) and rubust invesment promotion framework. | i. To provide access to finacing for the early-State Development of PPP projects, including fisibility studies, business case analysis and transaction advisory support. ii. Enhence PPP Project viability. iii. Attract Additional funding. iv. Improve infrastruture Delivery. v. Promote innovations. | i. Identification of PPP Projects by MDAs, first Quarter 2025. ii. Define Elegibility careterial first Quarter 2025. iii. Lunch funding appliacation processes first Quarter 2025. Vi. seek Governors approval first Quarter 2025. | Sokoto Bureau for Public Procurement and Public Procurment Parnership, Sokoto Invesment Company Limited. | State House of Assembly, Ministry of Justice, EXCO, Chamber of Commerce | 50000000 | 1st January 2025 | 31 Decemeber 2025 | Completed | i. PPP Project has been identified in various MDAs as plan. Ii. Eligibility cretaria for the PPP projects has been defined. Iii. Funding application processes for the PPP projects has been lunched. Iv. Governors approval has been obtained. | Intensify the attraction of investors for the PPP Projects and additional funding from the Government. Furthermore, improved infrastructured delivery and promote innovations
4 | Enabling firm operation and regulatory reforms | Improve transparency, accountability and efficiency in service delivery of 5 Business Enabling Enterprises state MDAs while promoting openness. | i. The 5 Business Enabling Enterprises (BEEs) namely Bureu for Public Procurement and Public Private Partnership (BPP & PPP), Sokoto Water Board, Sokoto Urban and Regional Planning Board, Internal Revenue Service and Ministry of Commerce, Trade and Industry to contine to publish their processes fees and service level agreement (SLAs). ii. The 5 BEEs to continue in improving their Grevience Redress mechanism by using advance digital technology that will | i. The Process of Obtaining Business presmise Registration should within 24 Hours after all relevant payment of Revenue, ii. Obtaining BPPP Clearance and Certification within 48 Hours. iii. Water Borad Permit also within 48 Hours. vi. Revenue Clearance should be within 24 Hours after payment of all revenues. v. Urban and Regional Planing Bord Certification will be processed and issued within 48 Hours. iii. BEEs should ensure the prompt and timely | SOGIS, Sokoto Interal Revenue, SURPB, SSWB, BPP & PPP and Minitry of Commerce, Ministry off Agriculture | Ministry of Commerce, Trade and Industy | 100000000 | 1st January 2025 | 31 Decemeber 2025 | Completed | i. Business premises Registration is now within 24 hours after all relevants payments of revenue. ii. BPP Clearing certificate can be obatined within 24 hours. iii. Water connection permit is also within 24 hours. iv. Revenue clearance Ceritifcate after payment can be received within 24 hours. v. Building Permit can be processess and issued within 24 hours. | All BEEs processesing and Issuence of variours Certificate will be sustained within 24 hours or less.
5 | Increased transparency of fees and levies for inter-state trade and increased exporter certification | Increase transperancy and numbers of firms that obtained export certificates from NEPC by 20% | i. Standardize fees for inter state trade ii. Create unified system for export certification iii. Implement regular audit. | i. We have 150 registered Exporters to be increased to 200 registered Exporters in the State. Ii. The process of registration expected to be reduce from one week to real time 24 hours. Iii. After the approval the Exporters will be able to generate and print online. | Ministry of Commerce, Trade and Industry | Custums Department, IRS, VIO Office | 40000000 | 1st January 2025 | 31 Decemeber 2025 | Completed | i. As at 31 Decemebr 2025 we a total 494 registered exports which is above 200 targeted. Ii. The registration of Exporters is now within 24 Hours after all relevants document and payments evidence have been submitted. Iii. Exporters can now generate there Certificate online. | To ensure continues timely processing of the Exports registration Certificate .
6 | Simplification of State and Local Business Tax Regimes | To simplify and make it easy to understand and make payment for taxes in the state through sokoto State Internal Revnue Services. | i. Regular Review and revise tax code ii. Implement a unified tax filling system iii. Train tax officials and businesses. iv. Sensitization and public awareness. | i. Cost of Taxes are available real time (24 Hours) in all our BEEs first Quarter 2025 ii. Generatiing of payment schedule is also real time (24 hours) in all BEEs, first Quarter 2025. iii. Payment can be made in any available Banks include Online payment | Internal Revenue Services, Local Government Councils | 1. Water Board, Ministry of Commerce, BPP & PPP and SURPB | 70000000 | 1st January 2025 | 31 Decemeber 2025 | Completed | i Cost of texes are available real time (24 hours) in all our BEEs. Ii Payment schedules are generated real time (24 hours) in all BEEs. Iii Payments are being made in any available banks including online payment. | To maintain and continuing reviewing in line with Federal Government Tax legislations.
7 | Quick determinatio n of commercial disputes | i. To Provide Access to Justice to the Parties. ii. Decentralizati on of the Existing Small Claims Court to each of the Three Senatorial Zones out of the five operations Courts in the | i. Sensitization to the public on the existence of the small Claims Courts in the State. ii. Posting of the small claims court judge to each of the senatorial zones by July 2025. iii. Monitoring and evaluation of small claim courts. iv. To determine a small claims suite within the stipulated time per practice | i. Dispense at least 100 small claims cases within the year. ii. to increase business confidence in the society by quick dispensation of the small claims cases iii. minimized time and cost with 60 days including appeal resolution. iv. To attract more investors to the State at least 15 per month. | Hight court of Justice | Ministry of Justice and State House of Assembly | 50000000 | 1st January 2025 | 31 Decemeber 2025 | Completed | i Morethan 100 small claims cases were dispense within the year under review. ii Business confidence within our society has substaicialy increase due to despansation of small claim court cases. Iii Case hearing and appeals are now dispense within 60 days. iv More investors has invested due to the confidence and trust they have on the court system in despensation of justice. | Continuous sensitization of the general public on the existance of the small claim couts in the state. Furthermore, there is future addition of small claim courts especially in the areas with high population and markets.